## How To Use
Project Resource Sheet 관리
1. New Project Sheet Creation
| A | Temp. V00 sheet를 copy하여 sheet 이름을 수정하여 >< (검정색 화살표) 사이로 sheet를 옮긴다.
| B | 검정색 화살표 사이에 Sheet를 넣으면 자동으로 SheetMerge로 Data가 통합된다.
| C | Temp. V00
|  | * | 연두색 - 입력 혹은 선택 항목
|  | * | 회색 - 자동입력
|  | 1 | Dropdown menu 에서 project를 선택하면 B1의 Project IO / B열 Status / C열 Project 내용이 자동으로 선택된다. - by PMO
|  | 2 | Dropdown menu 에서 Name을 선택하면 D열/E열/F열의 내용이 자동으로 선택된다. - by functions or PMO
|  | 3 | Gate5/Gate6 일정을 기재한다. (년/월 기재) - by PMO
|  | 4 | 월별 HC를 입력한다. - by functions
|  | 5 | 마지막 라인에 전체 project Gate plan 일정을 입력한다. 예) G1, G2….. - by PMO
2. Summary Sheet 설명
| A | SheetMerge |  | Do Not Change Anything | 입력한 project sheet의 모든 값들이 자동으로 통합되는 database sheet
| B | P1_정원 |  | Pivot Sheet | The number of available HC
| C | P2_부서 |  | Pivot Sheet | 정원 대비 forecast demand 차이
| D | P3_PRJ |  | Pivot Sheet | 프로젝트 별 forecast 현황
| F | P3_PRJ engineer gap |  | Pivot Sheet | Project allocation 별 engineer resource gap
| E | P4_Name |  | Pivot Sheet | 부서별 allocation 현황
| G | Project IO |  | Owner only allows changes | Owner - Jinney L | Project status / IO list
| H | 정원 |  | Owner only allows changes | Owner - Jinney L / Mogen S / Dorothy N |  | IS 총인원
99. Revision Note
| Ver. |  | Date | Description
| V1 |  | 2025-07-15 | 양식 변경
| V1.1 |  | 2025-07-15 | Excel Error 복구
| V1.2 |  | 2025-07-23 | PJT Lifecycle
1
2
3
4
5

## Temp. V00
|  |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-09 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | PJT Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 |  |  | 0 | Engineering | * Manager | * Eng Manager | JiYoung Son
2 |  |  | 0 | PMO | * Manager | * Manager | Jinney Lee
3 |  |  | 0 | PMO | PM | PM | Project manager
4 |  |  | 0 | NPI IS | * Manager | * Manager | Dorothy Noh
5 |  |  | 0 | NPI IS | System □ | Leader | Tech Lead
6 |  |  | 0 | NPI IS | System □ | System engineer | System engineer
7 |  |  | 0 | NPI IS | System □ | Service engineer | Service engineer
8 |  |  | 0 | NPI IS | Mechanical | Leader | Jeremy Park
9 |  |  | 0 | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer
10 |  |  | 0 | Control Eng. | * Manager | * Manager | Mogen Seo
11 |  |  | 0 | Control Eng. | Software | Leader | Gerald Park
12 |  |  | 0 | Control Eng. | Software | Software engineer | Software engineer
13 |  |  | 0 | Control Eng. | Software | SW test engineer | SW test engineer
14 |  |  | 0 | Control Eng. | Electrical | Leader | Joshua Im
15 |  |  | 0 | Control Eng. | Electrical | Electrical engineer | Electrical engineer
16 |  |  | 0 | 0 | 0 | 0
17 |  |  | 0
18 |  |  | 0
19 |  |  | 0 |  |  |  | Gate Plan |  |  | G2 |  |  | G5 |  | G6

## SheetMerge
No | Status | PJT Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Planning | Ganymede support - PCCA | NPI IS | System □ | System engineer | System engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Ashley Yun | 0 | 0 | 0 | 0.3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
3 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Rachel Bae | 0 | 0 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
4 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | SW test engineer | Amelia An | 0 | 0 | 1 | 1 | 0.9 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
5 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Roy Choi | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
6 | Active | Planning | Unify support | Control Eng. | Software | Leader | Gerald Park | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0
7 | Active | Planning | Unify support | Control Eng. | Software | Software engineer | Rachel Bae | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Planning | Unify support | Control Eng. | Software | SW test engineer | Amelia An | 0 | 0 | 0 | 0 | 0.1 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
9 | Active | Complete | R&D General - Legacy/TSG | NPI IS | System 1 | Technician | Robin Park | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Lead | CatOX Alpha design | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 0 | 0 | 0 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Cancelled | Cancelled | Hermes | Control Eng. | Software | Software engineer | Roy Choi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Cancelled | Cancelled | Hermes | Control Eng. | Software | SW test engineer | Moonsu Cho | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | LPLN TOP 150 support | NPI IS | System 3 | Tech Lead | Grace Ji | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | System engineer | Ricky Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | Service engineer | Chan Hwang | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Active | Micron A&D | PMO | * Manager | * Manager | Jinney Lee | 2025-03-26 | 2025-03-26 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Active | Micron A&D | PMO | PM | PM | Eugene Lee | 2025-03-26 | 2025-03-26 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.1 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Active | Micron A&D | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-03-26 | 2025-03-26 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | Micron A&D | NPI IS | Mechanical | Leader | Jeremy Park | 2025-03-26 | 2025-03-26 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0.5 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 2025-03-26 | 2025-03-26 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2025-03-26 | 2025-03-26 | 0 | 0 | 1 | 0.2 | 0 | 0 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | Micron A&D | NPI IS | System 2 | Tech Lead | Chad Seo | 2025-03-26 | 2025-03-26 | 0.9 | 0.9 | 0.9 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | Micron A&D | NPI IS | System 2 | Tech Lead | Emma Kim | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0.7 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Jess Kim | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | Micron A&D | NPI IS | System 3 | System engineer | Tred Park | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Stella Lim | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | Micron A&D | NPI IS | System 2 | Service engineer | Sophie Kim | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | Micron A&D | Engineering | * Manager | * Eng Manager | JiYoung Son | 2025-03-26 | 2025-03-26 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | Micron A&D | Control Eng. | * Manager | * Manager | Mogen Seo | 2025-03-26 | 2025-03-26 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | Micron A&D | Control Eng. | Electrical | Leader | Joshua Im | 2025-03-26 | 2025-03-26 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | Micron A&D | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | Micron A&D | Control Eng. | Software | Leader | Gerald Park | 2025-03-26 | 2025-03-26 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | Micron A&D | Control Eng. | Software | Software engineer | Software engineer | 2025-03-26 | 2025-03-26 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | Micron A&D | Control Eng. | Software | SW test engineer | Moonsu Cho | 2025-03-26 | 2025-03-26 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Active | Micron A&D | NPI IS | System 1 | System engineer | Chloe Jeong | 2025-03-26 | 2025-03-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Kevin Ko | 2025-03-26 | 2025-03-26 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Active | Micron A&D | 0 | 0 | 0 | Gate Plan | 2025-03-26 | 2025-03-26 | 0 | Update | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Active | Tumalo Ph2 | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2026-04-01 | 2026-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Active | Tumalo Ph2 | PMO | * Manager | * Manager | Jinney Lee | 2026-04-01 | 2026-09-28 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Active | Tumalo Ph2 | PMO | PM | PM | Evan Lee | 2026-04-01 | 2026-09-28 | 0 | 0.5 | 0.5 | 0.8 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | Tumalo Ph2 | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-04-01 | 2027-09-28 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Tech Lead | Jacob Lee | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Tech Lead | William Lee | 2027-04-01 | 2027-09-28 | 0 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | Tumalo Ph2 | NPI IS | System 2 | System engineer | Harry Kwak | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0 | 0 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | System engineer | Noah Yeom | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | System engineer | Alyssa Park | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | System engineer | Anders You | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Service engineer | Fred Lee | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | Service engineer | Chan Hwang | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.4 | 0.4 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | Tumalo Ph2 | NPI IS | System 2 | System engineer | Kevin Ko | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | System engineer | Chloe Jeong | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | Technician | Robin Park | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Leader | Jeremy Park | 2027-04-01 | 2027-09-28 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Allie Park | 2027-04-01 | 2027-09-28 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Wayne Jo | 2027-04-01 | 2027-09-28 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Jayce Park | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Active | Tumalo Ph2 | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-04-01 | 2027-09-28 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Leader | Gerald Park | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Ethan Jung | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Roy Choi | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Active | Active | Tumalo Ph2 | Control Eng. | Software | SW test engineer | Dave Kim | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Active | Active | Tumalo Ph2 | Control Eng. | Software | SW test engineer | Moonsu Cho | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Owen Rim | 2027-04-01 | 2027-09-28 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Leader | Joshua Im | 2027-04-01 | 2027-09-28 | 0 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | May Kwon | 2027-04-01 | 2027-09-28 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2027-04-01 | 2027-09-28 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Active | Active | Tumalo Ph2 | 0 | 0 | 0 | Gate Plan | 2027-04-01 | 2027-09-28 | 0 | G2 | 0 | 0 | 0 | 0 | 0 | G3 | 0 | 0 | 0 | 0 | 0 | G4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | PMO | * Manager | * Manager | Jinney Lee | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | Tech Lead | Chad Seo | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | * Manager | * Manager | Dorothy Noh | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | System engineer | Kevin Ko | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | Service engineer | Sophie Kim | 0 | 0 | 0 | 0 | 0 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | System engineer | Jess Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Leader | Jeremy Park | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | * Manager | * Manager | Mogen Seo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | Leader | Gerald Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | Software engineer | Ashley Yun | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | SW test engineer | Moonsu Cho | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Electrical | Leader | Joshua Im | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Electrical | Electrical engineer | Dean Choi | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 3 | System engineer | Tred Park | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | 0 | 0 | 0 | Gate Plan | 0 | 0 | 0 | 0 | G2 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Active | Havasu | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2025-06-25 | 2025-12-22 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Active | Havasu | PMO | * Manager | * Manager | Jinney Lee | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Active | Havasu | PMO | PM | PM | Evan Lee | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | Havasu | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | Havasu | NPI IS | System 1 | Tech Lead | Michael Kim | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | Havasu | NPI IS | System 1 | System engineer | Ricky Kim | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | Havasu | NPI IS | System 1 | System engineer | Anders You | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | Havasu | NPI IS | System 1 | System engineer | Chloe Jeong | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | Havasu | NPI IS | System 1 | Service engineer | Judy Lee | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | Havasu | NPI IS | Mechanical | Leader | Jeremy Park | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | Havasu | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | Havasu | Control Eng. | * Manager | * Manager | Mogen Seo | 2025-06-25 | 2025-12-22 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | Havasu | Control Eng. | Software | Leader | Gerald Park | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | Havasu | Control Eng. | Software | Software engineer | Roy choi | 2025-06-25 | 2025-12-22 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | Havasu | Control Eng. | Software | SW test engineer | Moonsu Cho | 2025-06-25 | 2025-12-22 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | Havasu | Control Eng. | Electrical | Leader | Joshua Im | 2025-06-25 | 2025-12-22 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | Havasu | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0.5 | 0.3 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | Havasu | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2025-06-25 | 2025-12-22 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | Havasu | 0 | 0 | 0 | Gate plan | 2025-06-25 | 2025-12-22 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | 0 | Tumalo Ph1 | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2026-02-01 | 2026-08-30 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | 0 | Tumalo Ph1 | PMO | * Manager | * Manager | Jinney Lee | 2026-02-01 | 2026-08-30 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | 0 | Tumalo Ph1 | PMO | PM | PM | Yuro Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | Tumalo Ph1 | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-02-01 | 2026-08-30 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | Jacob Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | Grace Ji | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | Tumalo Ph1 | NPI IS | System 2 | System engineer | Harry Kwak | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.5 | 0.5 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | System engineer | Alyssa Park | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | System engineer | Noah Yeom | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | System engineer | Anders You | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Service engineer | Fred Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | Service engineer | Chan Hwang | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | Technician | Robin Park | 2026-02-01 | 2026-08-30 | 0.8 | 0.8 | 0.8 | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Leader | Jeremy Park | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Evan Yu | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Wayne Jo | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Esther Jeong | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | Tumalo Ph1 | Control Eng. | * Manager | * Manager | Mogen Seo | 2026-02-01 | 2026-08-30 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Leader | Gerald Park | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Ethan Jung | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Roy Choi | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Ashley Yun | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Rachel Bae | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Dave Kim | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Amelia An | 2026-02-01 | 2026-08-30 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Leader | Joshua Im | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | May Kwon | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2026-02-01 | 2026-08-30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | Active | Active | Tumalo Ph1 | 0 | 0 | 0 | Gate Plan | 2026-02-01 | 2026-08-30 | 0 | 0 | G4 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Active | HRS Integrates | PMO | * Manager | * Manager | Jinney Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Active | HRS Integrates | PMO | PM | PM | Eugene Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.9 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Active | HRS Integrates | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | HRS Integrates | NPI IS | System 2 | Tech Lead | Chad Seo | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | HRS Integrates | NPI IS | System 3 | Tech Lead | William Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | HRS Integrates | NPI IS | System 2 | Tech Lead | Emma Kim | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0.3 | 0.9 | 0.9 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | HRS Integrates | NPI IS | System 2 | Service engineer | Sophie Kim | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0.3 | 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | HRS Integrates | NPI IS | System 2 | System engineer | Kevin Ko | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | HRS Integrates | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0.3 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | HRS Integrates | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | HRS Integrates | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | HRS Integrates | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-03-30 | 2026-03-30 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | HRS Integrates | NPI IS | System 2 | System engineer | Harry Kwak | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | HRS Integrates | PMO | PM | PM | Yuro Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | HRS Integrates | 0 | 0 | 0 | Gate Plan | 2026-03-30 | 2026-03-30 | G2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Active | Active | HRS | Engineering | * Manager | * Eng Manager | JiYoung Son | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Active | Active | HRS | PMO | * Manager | * Manager | Jinney Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Active | Active | HRS | PMO | PM | PM | Project manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Active | Active | HRS | NPI IS | * Manager | * Manager | Dorothy Noh | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Active | Active | HRS | NPI IS | System 2 | Tech Lead | Emma Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Active | Active | HRS | NPI IS | System 2 | System engineer | Kevin Ko | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Active | Active | HRS | NPI IS | System 1 | System engineer | Chloe Jeong | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Active | Active | HRS | NPI IS | System 2 | Service engineer | Sophie Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Active | Active | HRS | NPI IS | 0 | Service engineer | Service engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Active | Active | HRS | NPI IS | Mechanical | Leader | Jeremy Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Active | Active | HRS | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Active | Active | HRS | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Active | Active | HRS | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Active | Active | HRS | Control Eng. | * Manager | * Manager | Mogen Seo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Active | Active | HRS | Control Eng. | Software | Leader | Gerald Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Active | Active | HRS | Control Eng. | Software | Software engineer | Software engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Active | Active | HRS | Control Eng. | Software | SW test engineer | SW test engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Active | Active | HRS | Control Eng. | Electrical | Leader | Joshua Im | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Active | Active | HRS | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Active | Active | HRS | NPI IS | System 2 | System engineer | Harry Kwak | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Active | Active | HRS |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Active | Active | HRS | 0 | 0 | 0 | Gate Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | Active | Active | HRS | 0 | 0 | 0 | Gate Plan | 0 | 0 | G2 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G3 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | potential | Opportunty | HRS 9N Upgarde | PMO | * Manager | * Manager | Jinney Lee | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | potential | Opportunty | HRS 9N Upgarde | PMO | PM | PM | Eugene Lee | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | potential | Opportunty | HRS 9N Upgarde | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | potential | Opportunty | HRS 9N Upgarde | NPI IS | System 2 | Tech Lead | Chad Seo | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | potential | Opportunty | HRS 9N Upgarde | NPI IS | System 2 | System engineer | Jess Kim | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | potential | Opportunty | HRS 9N Upgarde | NPI IS | System 1 | Service engineer | Judy Lee | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | potential | Opportunty | HRS 9N Upgarde | NPI IS | Mechanical | Leader | Jeremy Park | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | potential | Opportunty | HRS 9N Upgarde | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Software | Leader | Gerald Park | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Software | Software engineer | Software engineer | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Software | SW test engineer | SW test engineer | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Electrical | Leader | Joshua Im | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | potential | Opportunty | HRS 9N Upgarde | 0 | 0 | 0 | Gate Plan | 2027-01-25 | 2027-01-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G2 | 0 | 0 | 0 | 0 | 0 | Update | 0 | 0 | 0 | 0 | G5/G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | potential | Lead | CatOX | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0
2 | potential | Lead | CatOX | PMO | * Manager | * Manager | Jinney Lee | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0
3 | potential | Lead | CatOX | PMO | PM | PM | Yuro Lee | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
4 | potential | Lead | CatOX | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | potential | Lead | CatOX | NPI IS | System 1 | Tech Lead | Michael Kim | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
6 | potential | Lead | CatOX | NPI IS | System 2 | System engineer | Jess Kim | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
7 | potential | Lead | CatOX | NPI IS | System □ | System engineer | System engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
8 | potential | Lead | CatOX | NPI IS | System 3 | System engineer | Tred Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
9 | potential | Lead | CatOX | NPI IS | System 1 | Service engineer | Judy Lee | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
10 | potential | Lead | CatOX | NPI IS | System 1 | Technician | Robin Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | potential | Lead | CatOX | NPI IS | Mechanical | Leader | Jeremy Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | potential | Lead | CatOX | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
13 | potential | Lead | CatOX | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
14 | potential | Lead | CatOX | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0
15 | potential | Lead | CatOX | Control Eng. | Software | Leader | Gerald Park | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | potential | Lead | CatOX | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
17 | potential | Lead | CatOX | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | potential | Lead | CatOX | Control Eng. | Software | SW test engineer | SW test engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
19 | potential | Lead | CatOX | Control Eng. | Electrical | Leader | Joshua Im | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | potential | Lead | CatOX | Control Eng. | Electrical | Electrical engineer | Hana Lee | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
21 | potential | Lead | CatOX | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | potential | Lead | CatOX | 0 | 0 | 0 | Gate Plan | 2027-06-01 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G1 | 0 | G2 | 0 | 0 | 0 | G3 | 0 | 0 | 0 | 0 | G4 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0
1 | Plan | Lead | Kanara | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Plan | Lead | Kanara | PMO | * Manager | * Manager | Jinney Lee | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Plan | Lead | Kanara | PMO | PM | PM | Project manager | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Plan | Lead | Kanara | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Plan | Lead | Kanara | NPI IS | System □ | Leader | Tech Lead | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Plan | Lead | Kanara | NPI IS | System □ | System engineer | System engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Plan | Lead | Kanara | NPI IS | System □ | System engineer | System engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Plan | Lead | Kanara | NPI IS | System □ | System engineer | System engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Plan | Lead | Kanara | NPI IS | System □ | Service engineer | Service engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Plan | Lead | Kanara | NPI IS | Mechanical | Leader | Jeremy Park | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Plan | Lead | Kanara | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Plan | Lead | Kanara | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Plan | Lead | Kanara | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Plan | Lead | Kanara | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Plan | Lead | Kanara | Control Eng. | Software | Leader | Gerald Park | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Plan | Lead | Kanara | Control Eng. | Software | Software engineer | Software engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Plan | Lead | Kanara | Control Eng. | Software | SW test engineer | SW test engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Plan | Lead | Kanara | Control Eng. | Electrical | Leader | Joshua Im | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | Plan | Lead | Kanara | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | Plan | Lead | Kanara | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Plan | Lead | Kanara | 0 | 0 | 0 | Gate Plan | 2027-07-30 | 2027-12-27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G1 | 0 | 0 | G2 | 0 | 0 | 0 | 0 | G3/G4 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Complete | Launched | EUV Zenith Plus | PMO | * Manager | * Manager | Jinney Lee | 2025-11-30 | 2026-06-30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Complete | Launched | EUV Zenith Plus | PMO | PM | PM | Yuro Lee | 2025-11-30 | 2026-06-30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Complete | Launched | EUV Zenith Plus | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-11-30 | 2026-06-30 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Complete | Launched | EUV Zenith Plus | 0 | 0 | 0 | Gate Plan | 2025-11-30 | 2026-06-30 | G6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Cancelled | Lead | Carl Zeiss | PMO | * Manager | * Manager | Jinney Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Cancelled | Lead | Carl Zeiss | PMO | PM | PM | Project manager | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Cancelled | Lead | Carl Zeiss | NPI IS | * Manager | * Manager | Dorothy Noh | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | Tech Lead | Michael Kim | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Cancelled | Lead | Carl Zeiss | NPI IS | System □ | System engineer | System engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | Service engineer | Judy Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Cancelled | Lead | Carl Zeiss | NPI IS | Mechanical | Leader | Jeremy Park | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Cancelled | Lead | Carl Zeiss | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Cancelled | Lead | Carl Zeiss | Control Eng. | * Manager | * Manager | Mogen Seo | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | Leader | Gerald Park | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | Software engineer | Software engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | SW test engineer | SW test engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Cancelled | Lead | Carl Zeiss | Control Eng. | Electrical | Leader | Joshua Im | 0 | 0 | 0 | 0 | 0 | 0 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Cancelled | Lead | Carl Zeiss | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Cancelled | Lead | Carl Zeiss | 0 | 0 | 0 | Gate Plan | 0 | 0 | 0 | 0 | 0 | 0 | G2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | G5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## P1_정원
Total IS NPI | 46.9 | 46.9 | 46.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 47.9 | 47.9 | 47.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9
Sustaining SW | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Unify support SW | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
파견 LPLN SE | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total available HC | 40.4 | 40.4 | 40.4 | 39.4 | 39.4 | 39.4 | 39.4 | 40.1 | 41.1 | 41.1 | 41.1 | 41.1 | 41.1 | 42.1 | 45.1 | 45.1 | 46.1 | 46.1 | 46.1 | 46.1 | 46.1 | 46.1 | 46.1 | 46.1 | 46.1 | 46.1
행 레이블 | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-Mar | Sum of 27-Apr | Sum of 27-May | Sum of 27-Jun | Sum of 27-Jul | Sum of 27-Aug | Sum of 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Control Eng. | 13.5 | 13.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Engineering | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
NPI IS | 29 | 29 | 28 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
PMO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
총합계 | 46.9 | 46.9 | 46.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 47.9 | 47.9 | 47.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9
Engineer HC | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41 | 41
TSG/파견 SW | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8
LPLN 파견 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Available HC | 34.5 | 34.5 | 34.5 | 34.5 | 34.5 | 34.5 | 34.5 | 35.2 | 35.2 | 35.2 | 35.2 | 35.2 | 35.2 | 35.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2 | 38.2
Resource role - engineering only
행 레이블 | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-Mar | Sum of 27-Apr | Sum of 27-May | Sum of 27-Jun | Sum of 27-Jul | Sum of 27-Aug | Sum of 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Electrical engineer | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Mechanical engineer | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
PM | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Service engineer | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Software engineer | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
SW test engineer | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
System engineer | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Tech Lead | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Technician
총합계 | 41 | 41 | 41 | 40 | 40 | 40 | 40 | 40 | 41 | 41 | 41 | 41 | 41 | 42 | 42 | 42 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43
Resource role - All
행 레이블 | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-Mar | Sum of 27-Apr | Sum of 27-May | Sum of 27-Jun | Sum of 27-Jul | Sum of 27-Aug | Sum of 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Control Eng. | 13.5 | 13.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Engineering | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
NPI IS | 29 | 29 | 28 | 27 | 27 | 27 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29 | 29
PMO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
총합계 | 46.9 | 46.9 | 46.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 47.9 | 47.9 | 47.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9

## P2_부서
정원 - Plan | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Control Eng. | -3 | -2.5 | -4.1 | -3.9 | -3.8 | -4 | -3.5 | -2.8 | -4.1 | -2.8 | -2.6 | -2.6 | -2.6 | -2.6 | -2.6 | -3.6 | -2.5 | -2.5 | 5.4 | 8.7 | 8.7
Engineering | 0 | 0 | -0.1 | -0.1 | -0.1 | 0 | 0 | 0 | -0.1 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.3 | 0.3
NPI IS | 1.6 | -0.8 | 1 | 0.6 | 0.7 | 1.4 | 1.4 | 1.5 | -2.2 | 1 | 4.3 | 0.3 | 0.3 | 1.3 | 4.3 | 4.3 | 4.4 | 4.4 | 16 | 22.7 | 22.7
PMO | -0.4 | -0.5 | -0.8 | -0.7 | -0.6 | -0.2 | -0.2 | -0.2 | -0.9 | -0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 1.1 | 1.1 | 2.8 | 3.4 | 3.4
총합계 | -1.8 | -3.8 | -4 | -4.1 | -3.8 | -2.8 | -2.3 | -1.5 | -7.3 | -2.1 | 2.2 | -1.8 | -1.8 | -0.8 | 2.3 | 1.3 | 3.1 | 3.1 | 24.4 | 35.1 | 35.1
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project | (모두)
Status | (다중 항목)
행 레이블 | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Control Eng. | 16.5 | 16 | 18.6 | 18.4 | 18.3 | 18.5 | 18 | 17.3 | 18.6 | 17.3 | 17.1 | 17.1 | 17.1 | 17.1 | 17.1 | 18.1 | 18 | 18 | 10.1 | 6.8 | 6.8
Engineering | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.5 | 0.4 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1
NPI IS | 27.4 | 29.8 | 27 | 26.4 | 26.3 | 25.6 | 25.6 | 25.5 | 30.2 | 27 | 23.7 | 27.7 | 27.7 | 27.7 | 24.7 | 24.7 | 24.6 | 24.6 | 13 | 6.3 | 6.3
PMO | 4.4 | 4.5 | 4.8 | 4.7 | 4.6 | 4.2 | 4.2 | 4.2 | 4.9 | 4.3 | 3.6 | 3.6 | 3.6 | 3.6 | 3.5 | 3.5 | 2.9 | 2.9 | 1.2 | 0.6 | 0.6
총합계 | 48.7 | 50.7 | 50.9 | 50 | 49.7 | 48.7 | 48.2 | 47.4 | 54.2 | 49 | 44.7 | 48.7 | 48.7 | 48.7 | 45.6 | 46.6 | 45.8 | 45.8 | 24.5 | 13.8 | 13.8

## P3_PRJ total gap
| 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Total HC VS Plan | 46.9 | 46.9 | 46.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 47.9 | 47.9 | 47.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9
Total HC | 46.9 | 46.9 | 46.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 47.9 | 47.9 | 47.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9
Status | (다중 항목)
Resource Role | (모두)
행 레이블 | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
CatOX Alpha design | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ganymede support - PCCA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Havasu | 5.3 | 4.8 | 1.5 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HRS Integrates | 5.1 | 4.3 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Micron A&D | 4.4 | 8.4 | 9.5 | 10 | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R&D General - Legacy/TSG | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Tumalo Ph1 | 12.1 | 12.1 | 8.4 | 8.4 | 7.9 | 7.3 | 6.8 | 6.7 | 6.7 | 6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph2 | 9.6 | 9.6 | 12.4 | 12.4 | 12.6 | 13.2 | 13.2 | 13.2 | 14.2 | 16 | 16 | 16 | 16 | 16 | 16.4 | 16.4 | 15.6 | 15.6 | 0 | 0 | 0
Unify support | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 | 0.8
Gen3 EUV Zenith Plus 7SRC TSMC | 5.2 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LPLN TOP 150 support | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kanara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8 | 6.8 | 9.2 | 13.2 | 13.2 | 13.2 | 13.2 | 14.2 | 14.2 | 14.2 | 11 | 11 | 11
HRS | 0 | 2.2 | 12.2 | 11.7 | 11.7 | 12.7 | 12.7 | 12.7 | 12.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.2 | 13.2 | 13.2 | 13.2 | 10.7 | 0 | 0
총합계 | 48.7 | 50.7 | 50.9 | 50 | 49.7 | 48.7 | 48.2 | 47.4 | 54.2 | 49 | 44.7 | 48.7 | 48.7 | 48.7 | 45.6 | 46.6 | 45.8 | 45.8 | 24.5 | 13.8 | 13.8

## P3_PRJ engineer gap
Total HC VS Plan | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | Sum of 26-Sep | Sum of 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | 합계 : 27-Mar | 합계 : 27-Apr | Sum of 27-May | Sum of 27-Jun | 합계 : 27-Jul | 합계 : 27-Aug | 합계 : 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Electrical engineer | 0 | -0.5 | -0.3 | -0.1 | -0.1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 3 | 3.5 | 3.5
Mechanical engineer | 1 | -0.5 | 1 | 0 | 0 | 0 | 0 | 0 | -1 | -0.5 | 0 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -2 | -1.5 | -1.5 | -0.5 | 2.5 | 5 | 5
PM | -0.2 | -0.1 | -0.7 | -0.6 | -0.6 | -0.4 | -0.4 | -0.4 | -0.9 | -0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 1 | 1 | 1 | 2 | 2.5 | 2.5
Service engineer | 0.3 | 0 | -0.5 | -0.2 | -0.2 | 0 | 0 | 0 | 0 | -0.6 | 0 | -1 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 4
Software engineer | -2.2 | -1.7 | -2.7 | -2.7 | -2.7 | -2.2 | -2.2 | -1.7 | -2.7 | -3.5 | -3.5 | -3.5 | -3.5 | -3.5 | -3.5 | -3.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | -2.5 | 0.5 | 2.5 | 2.5
SW test engineer | -1 | -0.5 | -1 | -1 | -1 | -2 | -1.5 | -1.5 | -1.5 | -1 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | 0.5 | 1 | 1
System engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2 | 0.3 | 2 | 1 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3.5 | 3.5 | 3.5 | 5.5 | 7 | 7
Tech Lead | 0.3 | 0 | 0.5 | 0.8 | 0.8 | 1 | 1 | 1 | 1 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 3.5 | 4 | 4 | 4 | 5.5 | 6 | 6
Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
총합계 | -1.8 | -3.3 | -3.7 | -3.8 | -3.8 | -3.6 | -3.1 | -2.6 | -7.1 | -2.8 | 1 | -3 | -3 | -2 | 1 | 0 | 1 | 1 | 1.5 | 1.5 | 4 | 4 | 6.5 | 21.5 | 31.5 | 31.5
Functional Engineer Requirement
Resource Department | (모두)
Status | (다중 항목)
PJT Lifecycle | (모두)
Project | (다중 항목)
행 레이블 | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | Sum of 26-Sep | Sum of 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | 합계 : 27-Mar | 합계 : 27-Apr | Sum of 27-May | Sum of 27-Jun | 합계 : 27-Jul | 합계 : 27-Aug | 합계 : 27-Sep | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
Electrical engineer | 4 | 4.5 | 5.3 | 5.1 | 5.1 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4.5 | 4.5 | 4 | 2 | 1.5 | 1.5
Mechanical engineer | 6 | 7.5 | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 7.5 | 7 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 8.5 | 8.5 | 7.5 | 4.5 | 2 | 2
PM | 3.2 | 3.1 | 3.7 | 3.6 | 3.6 | 3.4 | 3.4 | 3.4 | 3.9 | 3.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2.5 | 2.5 | 2 | 2 | 2 | 1 | 0.5 | 0.5
Service engineer | 3.7 | 4 | 4.5 | 4.2 | 4.2 | 4 | 4 | 4 | 4 | 4.6 | 4 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0
Software engineer | 6.2 | 5.7 | 6.7 | 6.7 | 6.7 | 6.2 | 6.2 | 5.7 | 6.7 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 4.5 | 2.5 | 2.5
SW test engineer | 4 | 3.5 | 4 | 4 | 4 | 5 | 4.5 | 4.5 | 4.5 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2.5 | 2 | 2
System engineer | 10 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 11 | 8.7 | 7 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 6.5 | 6.5 | 6.5 | 4.5 | 3 | 3
Tech Lead | 5.7 | 6 | 5.5 | 5.2 | 5.2 | 5 | 5 | 5 | 5 | 4 | 3.5 | 3.5 | 3.5 | 3.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 2 | 0.5 | 0 | 0
Technician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
총합계 | 42.8 | 44.3 | 44.7 | 43.8 | 43.8 | 43.6 | 43.1 | 42.6 | 48.1 | 43.8 | 40 | 44 | 44 | 44 | 41 | 42 | 42 | 42 | 41.5 | 41.5 | 39 | 39 | 36.5 | 21.5 | 11.5 | 11.5
Project Requirement
Resource Department | (모두)
Status | (다중 항목)
PJT Lifecycle | (모두)
행 레이블 | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Nov | 합계 : 26-Dec | Sum of 27-Jan | Sum of 27-Feb | Sum of 27-May | Sum of 27-Jun | Sum of 27-Oct | Sum of 27-Nov | Sum of 27-Dec
CatOX Alpha design | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ganymede support - PCCA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Havasu | 4.6 | 4.1 | 1.5 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HRS Integrates | 4.9 | 3.7 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Micron A&D | 3.4 | 7.1 | 8.1 | 8.6 | 8.6 | 7.6 | 7.6 | 7.6 | 7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R&D General - Legacy/TSG | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Tumalo Ph1 | 10.4 | 10.5 | 6.9 | 6.9 | 6.8 | 6.3 | 5.8 | 5.8 | 5.8 | 5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph2 | 8.5 | 8.4 | 11 | 11 | 11.1 | 11.7 | 11.7 | 11.7 | 12.7 | 14.5 | 14.5 | 14.5 | 15 | 15 | 14.5 | 14.5 | 0 | 0 | 0
Unify support | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Gen3 EUV Zenith Plus 7SRC TSMC | 4.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LPLN TOP 150 support | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kanara | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 5 | 11 | 11 | 11 | 12 | 12 | 12 | 9 | 9 | 9
HRS | 0 | 2 | 11 | 10.5 | 10.5 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 12.5 | 12.5 | 12.5 | 12.5 | 10 | 0 | 0
총합계 | 42.8 | 44.3 | 44.7 | 43.8 | 43.8 | 43.6 | 43.1 | 42.6 | 48.1 | 43.8 | 44 | 44 | 41 | 42 | 41.5 | 41.5 | 21.5 | 11.5 | 11.5

## P4_Name
Status | Active
Resource Department | (다중 항목)
행 레이블 | 합계 : 25-Jun | 합계 : 25-Jul | 합계 : 25-Aug | 합계 : 25-Sep | 합계 : 25-Oct | 합계 : 25-Nov | 합계 : 25-Dec | 합계 : 26-Jan | 합계 : 26-Feb | 합계 : 26-Mar | 합계 : 26-Apr | 합계 : 26-May | 합계 : 26-Jun | 합계 : 26-Jul | 합계 : 26-Aug | 합계 : 26-Sep | 합계 : 26-Oct | 합계 : 26-Nov | 합계 : 26-Dec
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
* Manager | 2.6 | 2.9 | 3.1 | 3.1 | 3.1 | 3.1 | 3.4 | 3.2 | 3.2 | 2.9 | 2.4 | 2.4 | 2.3 | 2.3 | 1.7 | 1.2 | 1.2 | 1.2 | 1.2
* Eng Manager | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2
JiYoung Son | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2
* Manager | 2.1 | 2.5 | 2.7 | 2.7 | 2.7 | 2.7 | 3 | 2.7 | 2.7 | 2.4 | 2 | 2 | 1.9 | 1.9 | 1.4 | 1 | 1 | 1 | 1
Dorothy Noh | 0.8 | 1 | 1 | 1 | 1 | 1 | 1.1 | 1.1 | 1.1 | 1 | 0.8 | 0.8 | 0.7 | 0.7 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4
Jinney Lee | 0.8 | 1 | 1.2 | 1.2 | 1.2 | 1.2 | 1.4 | 1.1 | 1.1 | 1 | 0.8 | 0.8 | 0.8 | 0.8 | 0.6 | 0.4 | 0.4 | 0.4 | 0.4
Mogen Seo | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2
Electrical | 5 | 5 | 5 | 5.3 | 4.8 | 4.8 | 5.3 | 6.2 | 6 | 6 | 5.8 | 5.8 | 5.8 | 5.8 | 4.5 | 3.3 | 3.3 | 3.3 | 3.3
Mechanical | 5.8 | 7.9 | 9.6 | 8 | 7 | 7 | 8.7 | 6.9 | 6.9 | 6.9 | 6.8 | 6.8 | 6.8 | 7.8 | 7 | 6.4 | 6.4 | 6.4 | 6.4
PM | 3 | 3.5 | 3 | 3 | 3 | 3.2 | 3.1 | 3.7 | 3.6 | 3.6 | 3.4 | 3.4 | 3.4 | 3.4 | 2.5 | 2 | 2 | 2 | 2
Software | 9.7 | 10.8 | 10.8 | 11.8 | 12 | 11.2 | 10.2 | 11.9 | 11.9 | 11.9 | 12.3 | 11.8 | 11.1 | 11.1 | 11.2 | 10.1 | 10.1 | 10.1 | 10.1
Leader | 1.2 | 1 | 0.8 | 0.8 | 1 | 1 | 1 | 1.2 | 1.2 | 1.2 | 1.1 | 1.1 | 0.9 | 0.9 | 0.7 | 0.6 | 0.6 | 0.6 | 0.6
Software engineer | 5.5 | 6.3 | 6.5 | 7 | 7 | 6.2 | 5.7 | 6.7 | 6.7 | 6.7 | 6.2 | 6.2 | 5.7 | 5.7 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
Ashley Yun | 0 | 0.3 | 1 | 1.5 | 1.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R&D General - Legacy/TSG | 0 | 0.3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gen3 EUV Zenith Plus 7SRC TSMC | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ethan Jung | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tumalo Ph1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Rachel Bae | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
R&D General - Legacy/TSG | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tumalo Ph1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unify support | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Roy Choi | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 2 | 1.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
Havasu | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R&D General - Legacy/TSG | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tumalo Ph1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
Software engineer | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2.2 | 2 | 2 | 2 | 2 | 2
Micron A&D | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0
HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Owen Rim | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tumalo Ph2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
SW test engineer | 3 | 3.5 | 3.5 | 4 | 4 | 4 | 3.5 | 4 | 4 | 4 | 5 | 4.5 | 4.5 | 4.5 | 4 | 3 | 3 | 3 | 3
Amelia An | 1 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1
R&D General - Legacy/TSG | 1 | 1 | 0.9 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Tumalo Ph1 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Unify support | 0 | 0 | 0.1 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Dave Kim | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tumalo Ph1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Moonsu Cho | 1 | 1 | 1 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5
Havasu | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HRS Integrates | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Micron A&D | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
Tumalo Ph1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Tumalo Ph2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Gen3 EUV Zenith Plus 7SRC TSMC | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SW test engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
System □ | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System 1 | 7 | 7 | 6 | 5 | 4 | 5.4 | 6 | 5 | 4.4 | 4.4 | 4 | 4 | 4 | 4 | 4.5 | 4 | 4 | 4 | 4
Service engineer | 2 | 2 | 2 | 1.5 | 1.5 | 1.7 | 2 | 1.5 | 1.2 | 1.2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Chan Hwang | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Judy Lee | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System engineer | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3.5 | 3 | 3 | 3 | 3
Anders You | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.5 | 1 | 1 | 1 | 1
Chloe Jeong | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Ricky Kim | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Technician | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Robin Park | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech Lead | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michael Kim | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5 | 0.2 | 0.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
System 2 | 6 | 6 | 6 | 6.5 | 7 | 7 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 4 | 4
Service engineer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sophie Kim | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
System engineer | 3 | 3 | 3 | 3.5 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2
Harry Kwak | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
HRS Integrates | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph1 | 1 | 1 | 0.6 | 0.6 | 0.5 | 0.5 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tumalo Ph2 | 0 | 0 | 0.4 | 0.4 | 0 | 0 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
HRS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Jess Kim | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Kevin Ko | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Stella Lim | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Micron A&D | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tech Lead | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
Chad Seo | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Emma Kim | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
System 3 | 6.1 | 7 | 7 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5.8 | 3.5 | 3.5 | 3.5 | 3.5
Service engineer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6 | 1 | 1 | 1 | 1
Fred Lee | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.6 | 1 | 1 | 1 | 1
System engineer | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.2 | 0 | 0 | 0 | 0
Alyssa Park | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0 | 0 | 0 | 0
Noah Yeom | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.6 | 0 | 0 | 0 | 0
Tred Park | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Tech Lead | 2.1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2.5 | 2.5 | 2.5 | 2.5
Grace Ji | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Jacob Lee | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
William Lee | 0.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
총합계 | 45.2 | 50.1 | 50.5 | 48.7 | 47.9 | 48.7 | 50.7 | 50.9 | 50 | 49.7 | 48.7 | 48.2 | 47.4 | 48.4 | 42.2 | 35.5 | 35.5 | 35.5 | 35.5

## Project IO
Do Not Change This Sheet |  | Last Update | 2025-09-09
Project | Project JO | PCAS Status | Project Lifecycle |  | Terminology of Project Lifecycle Status in SUN PMO
CatOX Alpha design | 407060 | Active | Lead |  | * Define status in terms of Start to End of Phase Gate
Ganymede support - PCCA | 407078 | Active | Planning |  | 예) Gate0가 끝나고 Gate1까지는 "Opportunity"
Havasu | 406399 | Active | Active
HRS Integrates | 406403 | Active | Active
Micron A&D | 406886 | Active | Active
PCAS Pre-Gate 1 Support(SIA) | 407057 | Active | Lead
R&D General - Legacy/TSG | 406442 | Active | Complete
Tumalo Ph1 | 406437 | Active | Active
EUV Zenith Plus | 406372 | Complete | Launched
Tumalo Ph2 | 407039 | Active | Active
Unify support | 407053 | Active | Planning
Carl Zeiss | TBC | Cancelled | Lead
CatOX | TBC | potential | Lead
HRS 9N Upgarde | TBC | potential | Opportunty
Kanara | TBC | Plan | Lead
HRS | TBC | Active | Active |  | Projedt Status 정의 - PCAS IS NPI 기준
Hermes | 407110 | Cancelled | Cancelled | Decision made on 2025.10 | Active | PCP에 의해 승인받고 IS NPI에서 진행하고 있는 commit project - Current product 지원 포함
Gen3 EUV Zenith Plus 7SRC TSMC | 407140 | Active | ETO |  | Complete | 완료된 project - Gate6 or Gate5 pass로 TSG hand-over가 완료된 project
Pre CPR for IS | 407057 | Active | Opportunty |  | Plan | Pre-Gate1(Gate2) 로 NPI Project 시작 전 PCAS NPI에서 project(support) 진행을 협의 및 검토 중인 단계
LPLN TOP 150 support | 407154 | Active | Active |  | Potential | Gate0 단계 혹은 RFQ 단계의 project로 NPI 에서 진행하는 것이 협의되지 않은 상태의 모든 project or support

## 정원
| 정원 | [6 empty] | SuM | 47.9 | 47.9 | 48.9 | 47.9 | 47.9 | 46.9 | 46.9 | 46.9 | 45.9 | 45.9 | 45.9 | 45.9 | 45.9 | 46.9 | 46.9 | 46.9 | 46.9 | 46.9 | 47.9 | 47.9 | 47.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9 | 48.9
No | Status | Project | Name | Resource Department | Sub-Team | Resource Role | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 |  | 정원 | JiYoung Son | Engineering | * Manager | * Eng Manager |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
2 |  | 정원 | Jinney Lee | PMO | * Manager | * Manager |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 |  | 정원 | Eugene Lee | PMO | PM | PM |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 |  | 정원 | Evan Lee | PMO | PM | PM |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 |  | 정원 | Yuro Lee | PMO | PM | PM |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 |  | 정원 | Dorothy Noh | NPI IS | * Manager | * Manager |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 |  | 정원 | Michael Kim | NPI IS | System 1 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 |  | 정원 | Anders You | NPI IS | System 1 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Move | 정원 | Robin Park | NPI IS | System 1 | Technician |  |  | 1 | 1 | 1 | 1
10 |  | 정원 | Ricky Kim | NPI IS | System 1 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
11 |  | 정원 | Chloe Jeong | NPI IS | System 1 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 |  | 정원 | Judy Lee | NPI IS | System 1 | Service engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 |  | 정원 | Chan Hwang | NPI IS | System 1 | Service engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
14 |  | 정원 | Jacob Lee | NPI IS | System 3 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 |  | 정원 | Grace Ji | NPI IS | System 3 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
16 |  | 정원 | Noah Yeom | NPI IS | System 3 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
17 | Parental leave | 정원 | Tred Park | NPI IS | System 3 | System engineer | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 |  | 정원 | William Lee | NPI IS | System 3 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
19 |  | 정원 | Alyssa Park | NPI IS | System 3 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
20 |  | 정원 | Fred Lee | NPI IS | System 3 | Service engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
21 |  | 정원 | Chad Seo | NPI IS | System 2 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
22 |  | 정원 | Jess Kim | NPI IS | System 2 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
23 |  | 정원 | Kevin Ko | NPI IS | System 2 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
24 |  | 정원 | Emma Kim | NPI IS | System 2 | Tech Lead |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25 |  | 정원 | Harry Kwak | NPI IS | System 2 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
26 | Parental leave | 정원 | Stella Lim | NPI IS | System 2 | System engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
27 |  | 정원 | Sophie Kim | NPI IS | System 2 | Service engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
28 |  | 정원 | Jeremy Park | NPI IS | Mechanical | Leader |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
29 |  | 정원 | Allie Park | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
30 |  | 정원 | Wayne Jo | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
31 |  | 정원 | Jiny Park | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
32 | Move | 정원 | Evan Yu | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1
33 | Parental leave | 정원 | Jayce Park | NPI IS | Mechanical | Mechanical engineer | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
34 | Parental leave | 정원 | Esther Jeong | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
35 |  | 정원 | Sooyoung Song | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
36 |  | 정원 | Derek Cho | NPI IS | Mechanical | Mechanical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
37 |  | 정원 | Jayden Lee | NPI IS | Mechanical | Mechanical engineer |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
38 |  | 정원 | Mogen Seo | Control Eng. | * Manager | * Manager |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
39 |  | 정원 | Gerald Park | Control Eng. | Software | Leader |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
40 | Parental leave | 정원 | Ashley Yun | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
41 |  | 정원 | Ethan Jung | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
42 |  | 정원 | Rachel Bae | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
43 |  | 정원 | Dave Kim | Control Eng. | Software | SW test engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
44 |  | 정원 | Moonsu Cho | Control Eng. | Software | SW test engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
45 |  | 정원 | Amelia An | Control Eng. | Software | SW test engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
46 |  | 정원 | Owen Rim | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
47 |  | 정원 | Roy Choi | Control Eng. | Software | Software engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
48 |  | 정원 | Joshua Im | Control Eng. | Electrical | Leader |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
49 |  | 정원 | Andy Jang | Control Eng. | Electrical | Electrical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
50 |  | 정원 | May Kwon | Control Eng. | Electrical | Electrical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
51 |  | 정원 | Dean Choi | Control Eng. | Electrical | Electrical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
52 |  | 정원 | Hana Lee | Control Eng. | Electrical | Electrical engineer | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
53 |  | 정원 | Julia Mun | Control Eng. | Electrical | Electrical engineer |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
초안용 범례 (검은선 위쪽에 정원 등록 요망, 행 삽입/삭제 가능)
Gate plan
|  |  | Project Manager | PMO | PM | PM
|  |  | Tech Lead | NPI IS | System □ | Leader
|  |  | System engineer | NPI IS | System □ | System engineer
|  |  | Service engineer | NPI IS | System □ | Service engineer
|  |  | Mechanical engineer | NPI IS | Mechanical | Mechanical engineer
|  |  | Software engineer | Control Eng. | Software | Software engineer
|  |  | SW test engineer | Control Eng. | Software | SW test engineer
|  |  | Electrical engineer | Control Eng. | Electrical | Electrical engineer

## >
- | 정원 |  | Resource Plan | Ver. | 0 | Date | 2025-07-02
No | Status | Project | Name | Resource Department | Resource Role | Sub-Team | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28

## etc. V00
N/A | General Support |  |  | Resource Plan | Ver. | 0 | Date | 2025-07-02 | SUM | 3 | 4.3 | 5 | 4.5 | 6 | 7 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 5.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 2.8 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | Start | End | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Planning | Ganymede support - PCCA | NPI IS | System □ | System engineer | System engineer
2 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Ashley Yun |  |  | 0 | 0.3 | 1 | 1 | 1 | [16 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
3 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Rachel Bae |  |  | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
4 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | SW test engineer | Amelia An |  |  | 1 | 1 | 0.9 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
5 | Active | Complete | R&D General - Legacy/TSG | Control Eng. | Software | Software engineer | Roy Choi |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
6 | Active | Planning | Unify support | Control Eng. | Software | Leader | Gerald Park |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
7 | Active | Planning | Unify support | Control Eng. | Software | Software engineer | Rachel Bae | [6 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
8 | Active | Planning | Unify support | Control Eng. | Software | SW test engineer | Amelia An |  |  |  |  | 0.1 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
9 | Active | Complete | R&D General - Legacy/TSG | NPI IS | System 1 | Technician | Robin Park |  |  | 0.2 | 0.2 | 0.2 | 0.2
10 | Active | Lead | CatOX Alpha design | NPI IS | Mechanical | Mechanical engineer | Jiny Park |  |  |  | 1 | 1 | 0.5 | 0.5 | 0.5
11 | Cancelled | Cancelled | Hermes | Control Eng. | Software | Software engineer | Roy Choi
12 | Cancelled | Cancelled | Hermes | Control Eng. | Software | SW test engineer | Moonsu Cho
13 | Active | Active | LPLN TOP 150 support | NPI IS | System 3 | Tech Lead | Grace Ji | [6 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
14 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | System engineer | Ricky Kim | [6 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | Active | Active | LPLN TOP 150 support | NPI IS | System 1 | Service engineer | Chan Hwang | [6 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Micron A&D V00
Micron A&D | 406886 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 12.2 | 11.8 | 12.2 | 6.3 | 4.5 | 4.4 | 8.4 | 9.5 | 10 | 10 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Active | Micron A&D | PMO | * Manager | * Manager | Jinney Lee | 2025-03-26 | 2025-03-26 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
2 | Active | Active | Micron A&D | PMO | PM | PM | Eugene Lee | 2025-03-26 | 2025-03-26 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.1 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
3 | Active | Active | Micron A&D | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-03-26 | 2025-03-26 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
4 | Active | Active | Micron A&D | NPI IS | Mechanical | Leader | Jeremy Park | 2025-03-26 | 2025-03-26 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
5 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0.5 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 2025-03-26 | 2025-03-26 | 0.5 |  |  | 0.5 |  |  |  |  | 0.5 | 0.5
7 | Active | Active | Micron A&D | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2025-03-26 | 2025-03-26 |  |  | 1 | 0.2 |  |  | 1 | 0.5 | 0.5 | 0.5
8 | Active | Active | Micron A&D | NPI IS | System 2 | Tech Lead | Chad Seo | 2025-03-26 | 2025-03-26 | 0.9 | 0.9 | 0.9 |  |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Active | Active | Micron A&D | NPI IS | System 2 | Tech Lead | Emma Kim | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0.7 | 0.1 | 0.1
10 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Jess Kim | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
11 | Active | Active | Micron A&D | NPI IS | System 3 | System engineer | Tred Park | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Stella Lim | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | Active | Active | Micron A&D | NPI IS | System 2 | Service engineer | Sophie Kim | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 |  |  | 0.5
14 | Active | Active | Micron A&D | Engineering | * Manager | * Eng Manager | JiYoung Son | 2025-03-26 | 2025-03-26 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
15 | Active | Active | Micron A&D | Control Eng. | * Manager | * Manager | Mogen Seo | 2025-03-26 | 2025-03-26 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
16 | Active | Active | Micron A&D | Control Eng. | Electrical | Leader | Joshua Im | 2025-03-26 | 2025-03-26 | 0.3 | 0.3 | 0.3 |  |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
17 | Active | Active | Micron A&D | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2025-03-26 | 2025-03-26 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Active | Active | Micron A&D | Control Eng. | Software | Leader | Gerald Park | 2025-03-26 | 2025-03-26 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
19 | Active | Active | Micron A&D | Control Eng. | Software | Software engineer | Software engineer | 2025-03-26 | 2025-03-26 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
20 | Active | Active | Micron A&D | Control Eng. | Software | SW test engineer | Moonsu Cho | 2025-03-26 | 2025-03-26 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
21 | Active | Active | Micron A&D | NPI IS | System 1 | System engineer | Chloe Jeong | 2025-03-26 | 2025-03-26 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
22 | Active | Active | Micron A&D | NPI IS | System 2 | System engineer | Kevin Ko | 2025-03-26 | 2025-03-26 | [5 empty] | 0.5
23 | Active | Active | Micron A&D | 0 | 0 | 0 | Gate Plan | 2025-03-26 | 2025-03-26 |  | Update | [7 empty] | G5 |  |  |  | G6

## Tumalo Ph2 V00
Tumalo Ph2 | 407039 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 5.1 | 7.6 | 9.7 | 9.9 | 9.6 | 9.6 | 12.4 | 12.4 | 12.6 | 13.2 | 13.2 | 13.2 | 14.2 | 16 | 16 | 16 | 16 | 16 | 16.4 | 16.4 | 16.4 | 16.3 | 15.6 | 15.6 | 15.6 | 15.6 | 15.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Active | Tumalo Ph2 | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2026-04-01 | 2026-09-28 | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Active | Active | Tumalo Ph2 | PMO | * Manager | * Manager | Jinney Lee | 2026-04-01 | 2026-09-28 |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Active | Active | Tumalo Ph2 | PMO | PM | PM | Evan Lee | 2026-04-01 | 2026-09-28 |  | 0.5 | 0.5 | 0.8 | 0.8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
4 | Active | Active | Tumalo Ph2 | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-04-01 | 2027-09-28 |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
5 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Tech Lead | Jacob Lee | 2027-04-01 | 2027-09-28 |  |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
6 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Tech Lead | William Lee | 2027-04-01 | 2027-09-28 |  | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Active | Active | Tumalo Ph2 | NPI IS | System 2 | System engineer | Harry Kwak | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 |  |  | 0.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | System engineer | Noah Yeom | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
9 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | System engineer | Alyssa Park | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
10 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | System engineer | Anders You | 2027-04-01 | 2027-09-28 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
11 | Active | Active | Tumalo Ph2 | NPI IS | System 3 | Service engineer | Fred Lee | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | Service engineer | Chan Hwang | 2027-04-01 | 2027-09-28 |  |  | 0.4 | 0.4 | 0.5
13 | Active | Active | Tumalo Ph2 | NPI IS | System 2 | System engineer | Kevin Ko | 2027-04-01 | 2027-09-28
14 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | System engineer | Chloe Jeong | 2027-04-01 | 2027-09-28
15 | Active | Active | Tumalo Ph2 | NPI IS | System 1 | Technician | Robin Park | 2027-04-01 | 2027-09-28
16 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Leader | Jeremy Park | 2027-04-01 | 2027-09-28 |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
17 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Allie Park | 2027-04-01 | 2027-09-28 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Wayne Jo | 2027-04-01 | 2027-09-28 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
19 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Jayce Park | 2027-04-01 | 2027-09-28 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
20 | Active | Active | Tumalo Ph2 | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-04-01 | 2027-09-28 |  |  |  |  | 0.5 | 0.5
21 | Active | Active | Tumalo Ph2 | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-04-01 | 2027-09-28 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
22 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Leader | Gerald Park | 2027-04-01 | 2027-09-28 | [7 empty] | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
23 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Ethan Jung | 2027-04-01 | 2027-09-28 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
24 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Roy Choi | 2027-04-01 | 2027-09-28 | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25 | Active | Active | Tumalo Ph2 | Control Eng. | Software | SW test engineer | Dave Kim | 2027-04-01 | 2027-09-28 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
26 | Active | Active | Tumalo Ph2 | Control Eng. | Software | SW test engineer | Moonsu Cho | 2027-04-01 | 2027-09-28 | [10 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
26 | Active | Active | Tumalo Ph2 | Control Eng. | Software | Software engineer | Owen Rim | 2027-04-01 | 2027-09-28 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
27 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Leader | Joshua Im | 2027-04-01 | 2027-09-28 |  | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
28 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | May Kwon | 2027-04-01 | 2027-09-28 |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
29 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2027-04-01 | 2027-09-28
30 | Active | Active | Tumalo Ph2 | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2027-04-01 | 2027-09-28 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
31 | Active | Active | Tumalo Ph2 | 0 | 0 | 0 | Gate Plan | 2027-04-01 | 2027-09-28 |  | G2 | [5 empty] | G3 | [5 empty] | G4 | [8 empty] | G5 |  |  |  |  | G6

## Gen3 7SRC TFT
Gen3 EUV Zenith Plus 7SRC TSMC | 407140 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0.2 | 6.4 | 5.2 | 5.2 | 2.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | PMO | * Manager | * Manager | Jinney Lee |  |  |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
2 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | Tech Lead | Chad Seo | [5 empty] | 1 | 1 | 1 | 0.5
3 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | * Manager | * Manager | Dorothy Noh | [5 empty] | 0.1 | 0.1 | 0.1 | 0.1
5 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | System engineer | Kevin Ko | [5 empty] | 1 | 0 | 0
6 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | Service engineer | Sophie Kim | [5 empty] | 0.7 | 0 | 0
7 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 2 | System engineer | Jess Kim | [6 empty] | 0.5 | 0.5
8 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Leader | Jeremy Park | [5 empty] | 0.1 | 0.1 | 0.1
9 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | [5 empty] | 0.5 | 0.5 | 0.5
10 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | Mechanical | Mechanical engineer | Derek Cho | [5 empty] | 0.5
11 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | * Manager | * Manager | Mogen Seo
12 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | Leader | Gerald Park
13 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | Software engineer | Ashley Yun | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5
14 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Software | SW test engineer | Moonsu Cho | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5
15 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Electrical | Leader | Joshua Im | [5 empty] | 0.3 | 0.3 | 0.3
16 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | Control Eng. | Electrical | Electrical engineer | Dean Choi | [5 empty] | 1 | 0.5 | 0.5
17 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | NPI IS | System 3 | System engineer | Tred Park | [6 empty] | 1 | 1 | 1
18 | Active | ETO | Gen3 EUV Zenith Plus 7SRC TSMC | 0 | 0 | 0 | Gate Plan |  |  |  |  | G2 |  |  |  | G5

## Havasu V00
Havasu | 406399 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 11.5 | 9.7 | 8.2 | 5.9 | 4.4 | 5.3 | 4.8 | 1.5 | 0.6 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Active | Havasu | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2025-06-25 | 2025-12-22 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Active | Active | Havasu | PMO | * Manager | * Manager | Jinney Lee | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Active | Active | Havasu | PMO | PM | PM | Evan Lee | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.2 | 0.2 | 0.2 | 0.1 | 0.2 | 0.1 | 0.1
4 | Active | Active | Havasu | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
5 | Active | Active | Havasu | NPI IS | System 1 | Tech Lead | Michael Kim | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5 | 0.2 | 0.2
6 | Active | Active | Havasu | NPI IS | System 1 | System engineer | Ricky Kim | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.5
7 | Active | Active | Havasu | NPI IS | System 1 | System engineer | Anders You | 2025-06-25 | 2025-12-22 | 1 | 1 | 1
8 | Active | Active | Havasu | NPI IS | System 1 | System engineer | Chloe Jeong | 2025-06-25 | 2025-12-22 | 1 | 1 | 0.5 | 0.5 | 0.5 | 1 | 1
9 | Active | Active | Havasu | NPI IS | System 1 | Service engineer | Judy Lee | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 | 0.5 | 0.7 | 1 | 0.5 | 0.2 | 0.2
10 | Active | Active | Havasu | NPI IS | Mechanical | Leader | Jeremy Park | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
11 | Active | Active | Havasu | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 1 | 1 | 1
13 | Active | Active | Havasu | Control Eng. | * Manager | * Manager | Mogen Seo | 2025-06-25 | 2025-12-22 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
14 | Active | Active | Havasu | Control Eng. | Software | Leader | Gerald Park | 2025-06-25 | 2025-12-22 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
15 | Active | Active | Havasu | Control Eng. | Software | Software engineer | Roy choi | 2025-06-25 | 2025-12-22 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
16 | Active | Active | Havasu | Control Eng. | Software | SW test engineer | Moonsu Cho | 2025-06-25 | 2025-12-22 | 0.5 | 0.5 | 0.5 | 0.5
17 | Active | Active | Havasu | Control Eng. | Electrical | Leader | Joshua Im | 2025-06-25 | 2025-12-22 | 0.4 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
18 | Active | Active | Havasu | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2025-06-25 | 2025-12-22 | 1 | 1 | 1 | 0.5 |  |  | 0.5 | 0.3 | 0.1 | 0.1
19 | Active | Active | Havasu | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2025-06-25 | 2025-12-22 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5
20 | Active | Active | Havasu | 0 | 0 | 0 | Gate plan | 2025-06-25 | 2025-12-22 | G5 | [5 empty] | G6

## Tumalo Ph1 V00
Tumalo Ph1 | 406437 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 18 | 18.7 | 16.8 | 14.6 | 12.6 | 12.1 | 11.8 | 8.4 | 8.4 | 7.9 | 7.3 | 6.8 | 6.7 | 6.7 | 6.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active |  | Tumalo Ph1 | Engineering | * Manager | * Eng Manager | Jiyoung Son | 2026-02-01 | 2026-08-30 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Active |  | Tumalo Ph1 | PMO | * Manager | * Manager | Jinney Lee | 2026-02-01 | 2026-08-30 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
3 | Active |  | Tumalo Ph1 | PMO | PM | PM | Yuro Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
4 | Active | Active | Tumalo Ph1 | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-02-01 | 2026-08-30 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1
5 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | Jacob Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
6 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Tech Lead | Grace Ji | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 0.5
7 | Active | Active | Tumalo Ph1 | NPI IS | System 2 | System engineer | Harry Kwak | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.5 | 0.5 | 0.6
8 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | System engineer | Alyssa Park | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
9 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | System engineer | Noah Yeom | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
10 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | System engineer | Anders You | 2026-02-01 | 2026-08-30 |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
11 | Active | Active | Tumalo Ph1 | NPI IS | System 3 | Service engineer | Fred Lee | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6
12 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | Service engineer | Chan Hwang | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.6 | 0.6
13 | Active | Active | Tumalo Ph1 | NPI IS | System 1 | Technician | Robin Park | 2026-02-01 | 2026-08-30 | 0.8 | 0.8 | 0.8 | 0.8
14 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Leader | Jeremy Park | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.5 | 0.3 | 0.3 | 0.3 | 0.3 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
15 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Evan Yu | 2026-02-01 | 2026-08-30 | 1 | 1 | 1
16 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Wayne Jo | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
17 | Active | Active | Tumalo Ph1 | NPI IS | Mechanical | Mechanical engineer | Esther Jeong | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Active | Active | Tumalo Ph1 | Control Eng. | * Manager | * Manager | Mogen Seo | 2026-02-01 | 2026-08-30 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
19 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Leader | Gerald Park | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
20 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Ethan Jung | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1
21 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Roy Choi | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
22 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Ashley Yun | 2026-02-01 | 2026-08-30 |  |  |  |  | 0 | 0 | 0
23 | Active | Active | Tumalo Ph1 | Control Eng. | Software | Software engineer | Rachel Bae | 2026-02-01 | 2026-08-30 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
24 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Dave Kim | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
25 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-02-01 | 2026-08-30 | [11 empty] | 0.5 | 0.5 | 0.5 | 0.5
26 | Active | Active | Tumalo Ph1 | Control Eng. | Software | SW test engineer | Amelia An | 2026-02-01 | 2026-08-30 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
28 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Leader | Joshua Im | 2026-02-01 | 2026-08-30 | 0.3 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
29 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | May Kwon | 2026-02-01 | 2026-08-30 | 1 | 1 | 0.5
30 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2026-02-01 | 2026-08-30 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
31 | Active | Active | Tumalo Ph1 | Control Eng. | Electrical | Electrical engineer | Andy Jang | 2026-02-01 | 2026-08-30
32 | Active | Active | Tumalo Ph1 | 0 | 0 | 0 | Gate Plan | 2026-02-01 | 2026-08-30 |  |  | G4 | [5 empty] | G5 | [5 empty] | G6

## HRS Integrates V00
HRS Integrates | 406403 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0.5 | 0.5 | 0.5 | 1.3 | 5.3 | 5.1 | 4.6 | 0.4 | 0.4 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Active | HRS Integrates | PMO | * Manager | * Manager | Jinney Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.1 | 0.1 | 0.1
2 | Active | Active | HRS Integrates | PMO | PM | PM | Eugene Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.9 | 0.1 | 0.1 | 0.1 | 0.1
3 | Active | Active | HRS Integrates | NPI IS | * Manager | * Manager | Dorothy Noh | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.1 | 0.1 | 0.1
4 | Active | Active | HRS Integrates | NPI IS | System 2 | Tech Lead | Chad Seo | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1
5 | Active | Active | HRS Integrates | NPI IS | System 3 | Tech Lead | William Lee | 2026-03-30 | 2026-03-30 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
6 | Active | Active | HRS Integrates | NPI IS | System 2 | Tech Lead | Emma Kim | 2026-03-30 | 2026-03-30 |  |  |  | 0.3 | 0.9 | 0.9 | 0.5
7 | Active | Active | HRS Integrates | NPI IS | System 2 | Service engineer | Sophie Kim | 2026-03-30 | 2026-03-30 |  |  |  | 0.3 | 1 | 0.5 | 1
8 | Active | Active | HRS Integrates | NPI IS | System 2 | System engineer | Kevin Ko | [6 empty] | 1 | 0.5 | 1
9 | Active | Active | HRS Integrates | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | 2026-03-30 | 2026-03-30 |  |  |  | 0.3 | 0.5 | 0.5
10 | Active | Active | HRS Integrates | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | 2026-03-30 | 2026-03-30 | [6 empty] | 1
11 | Active | Active | HRS Integrates | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2026-03-30 | 2026-03-30 |  |  |  |  | 0.5 | 0.5
12 | Active | Active | HRS Integrates | Control Eng. | Software | SW test engineer | Moonsu Cho | 2026-03-30 | 2026-03-30 |  |  |  |  | 0.5 | 0.5
14 | Active | Active | HRS Integrates | NPI IS | System 2 | System engineer | Harry Kwak | [6 empty] | 0.5 | 0.5
15 | Active | Active | HRS Integrates | PMO | PM | PM | Yuro Lee | [8 empty] | 0.3
16 | Active | Active | HRS Integrates | 0 | 0 | 0 | Gate Plan | 2026-03-30 | 2026-03-30 | G2 | [8 empty] | G5 | [7 empty] | G5 |  |  |  | G6

## HRS
HRS | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-09 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 2.2 | 12.7 | 12.2 | 12.2 | 12.7 | 12.7 | 12.7 | 12.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.7 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 13.2 | 10.7 | 10.7 | 10.7 | 10.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | PJT Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Active | Active | HRS | Engineering | * Manager | * Eng Manager | JiYoung Son | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Active | Active | HRS | PMO | * Manager | * Manager | Jinney Lee | [9 empty] | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Active | Active | HRS | PMO | PM | PM | Project manager | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
4 | Active | Active | HRS | NPI IS | * Manager | * Manager | Dorothy Noh | [9 empty] | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
5 | Active | Active | HRS | NPI IS | System 2 | Tech Lead | Emma Kim | [8 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
6 | Active | Active | HRS | NPI IS | System 2 | System engineer | Kevin Ko | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Active | Active | HRS | NPI IS | System 1 | System engineer | Chloe Jeong | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
8 | Active | Active | HRS | NPI IS | System 2 | Service engineer | Sophie Kim | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Active | Active | HRS | NPI IS |  | Service engineer | Service engineer | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | Active | Active | HRS | NPI IS | Mechanical | Leader | Jeremy Park | [8 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
11 | Active | Active | HRS | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | [8 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
12 | Active | Active | HRS | NPI IS | Mechanical | Mechanical engineer | Sooyoung Song | [8 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | Active | Active | HRS | NPI IS | Mechanical | Mechanical engineer | Jiny Park | [8 empty] | 0.5 | 1 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
14 | Active | Active | HRS | Control Eng. | * Manager | * Manager | Mogen Seo | [9 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
15 | Active | Active | HRS | Control Eng. | Software | Leader | Gerald Park | [9 empty] | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
16 | Active | Active | HRS | Control Eng. | Software | Software engineer | Software engineer | [9 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
17 | Active | Active | HRS | Control Eng. | Software | SW test engineer | SW test engineer | [12 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
18 | Active | Active | HRS | Control Eng. | Electrical | Leader | Joshua Im | [9 empty] | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
19 | Active | Active | HRS | Control Eng. | Electrical | Electrical engineer | Electrical engineer | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
20 | Active | Active | HRS | NPI IS | System 2 | System engineer | Harry Kwak | [9 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
21 | Active | Active | HRS
22 | Active | Active | HRS | 0 | 0 | 0 | Gate Plan
23 | Active | Active | HRS | 0 | 0 | 0 | Gate Plan |  |  | G2 |  |  | G5 | [9 empty] | G3 |  |  |  |  | G5 | [6 empty] | G6
[23 empty] | G3 | [8 empty] | G5 | [5 empty] | G6
72500000
29000000
7250000
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HRS customer support

## HRS Integrated- 9N Upgrade V00
HRS 9N Upgarde | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1 | 5.1 | 6.1 | 6.6 | 8.1 | 8.1 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | potential | Opportunty | HRS 9N Upgarde | PMO | * Manager | * Manager | Jinney Lee | 2027-01-25 | 2027-01-25 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
2 | potential | Opportunty | HRS 9N Upgarde | PMO | PM | PM | Eugene Lee | 2027-01-25 | 2027-01-25 | [19 empty] | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3 | potential | Opportunty | HRS 9N Upgarde | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-01-25 | 2027-01-25 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
4 | potential | Opportunty | HRS 9N Upgarde | NPI IS | System 2 | Tech Lead | Chad Seo | 2027-01-25 | 2027-01-25 | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | potential | Opportunty | HRS 9N Upgarde | NPI IS | System 2 | System engineer | Jess Kim | 2027-01-25 | 2027-01-25 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | potential | Opportunty | HRS 9N Upgarde | NPI IS | System 1 | Service engineer | Judy Lee | 2027-01-25 | 2027-01-25 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | potential | Opportunty | HRS 9N Upgarde | NPI IS | Mechanical | Leader | Jeremy Park | 2027-01-25 | 2027-01-25 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.3 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
8 | potential | Opportunty | HRS 9N Upgarde | NPI IS | Mechanical | Mechanical engineer | Derek Cho | 2027-01-25 | 2027-01-25 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-01-25 | 2027-01-25 | [19 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
10 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Software | Leader | Gerald Park | 2027-01-25 | 2027-01-25 | [23 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
11 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Software | Software engineer | Software engineer | 2027-01-25 | 2027-01-25 | [19 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
12 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Software | SW test engineer | SW test engineer | 2027-01-25 | 2027-01-25 | [23 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
13 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Electrical | Leader | Joshua Im | 2027-01-25 | 2027-01-25 | [19 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
14 | potential | Opportunty | HRS 9N Upgarde | Control Eng. | Electrical | Electrical engineer | Dean Choi | 2027-01-25 | 2027-01-25 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | potential | Opportunty | HRS 9N Upgarde | 0 | 0 | 0 | Gate Plan | 2027-01-25 | 2027-01-25 | [19 empty] | G2 | [5 empty] | Update |  |  |  |  | G5/G6

## CatOX V00
CatOX | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8 | 7.8 | 7.8 | 7.8 | 10.9 | 10.9 | 12.3 | 13.3 | 13.5 | 13.5 | 13.5 | 13.5 | 13.5 | 13.2 | 13.1 | 13.1 | 13.1 | 13.1 | 13.1 | 12.5 | 11.4 | 11.4 | 11.4 | 11.4 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | potential | Lead | CatOX | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-06-01 | 2027-12-01 | [15 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | potential | Lead | CatOX | PMO | * Manager | * Manager | Jinney Lee | 2027-06-01 | 2027-12-01 | [15 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1
3 | potential | Lead | CatOX | PMO | PM | PM | Yuro Lee | 2027-06-01 | 2027-12-01 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | potential | Lead | CatOX | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-06-01 | 2027-12-01 | [15 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
5 | potential | Lead | CatOX | NPI IS | System 1 | Tech Lead | Michael Kim | 2027-06-01 | 2027-12-01 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | potential | Lead | CatOX | NPI IS | System 2 | System engineer | Jess Kim | 2027-06-01 | 2027-12-01 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | potential | Lead | CatOX | NPI IS | System □ | System engineer | System engineer | 2027-06-01 | 2027-12-01 | [15 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | potential | Lead | CatOX | NPI IS | System 3 | System engineer | Tred Park | 2027-06-01 | 2027-12-01 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | potential | Lead | CatOX | NPI IS | System 1 | Service engineer | Judy Lee | 2027-06-01 | 2027-12-01 | [21 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
10 | potential | Lead | CatOX | NPI IS | System 1 | Technician | Robin Park | 2027-06-01 | 2027-12-01
11 | potential | Lead | CatOX | NPI IS | Mechanical | Leader | Jeremy Park | 2027-06-01 | 2027-12-01 | [15 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
12 | potential | Lead | CatOX | NPI IS | Mechanical | Mechanical engineer | Jiny Park | 2027-06-01 | 2027-12-01 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | potential | Lead | CatOX | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-06-01 | 2027-12-01 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
14 | potential | Lead | CatOX | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-06-01 | 2027-12-01 | [15 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
15 | potential | Lead | CatOX | Control Eng. | Software | Leader | Gerald Park | 2027-06-01 | 2027-12-01 | [15 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
16 | potential | Lead | CatOX | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
17 | potential | Lead | CatOX | Control Eng. | Software | Software engineer | Software engineer | 2027-06-01 | 2027-12-01 | [15 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
18 | potential | Lead | CatOX | Control Eng. | Software | SW test engineer | SW test engineer | 2027-06-01 | 2027-12-01 | [22 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
19 | potential | Lead | CatOX | Control Eng. | Electrical | Leader | Joshua Im | 2027-06-01 | 2027-12-01 | [15 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
20 | potential | Lead | CatOX | Control Eng. | Electrical | Electrical engineer | Hana Lee | 2027-06-01 | 2027-12-01 | [15 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
21 | potential | Lead | CatOX | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-06-01 | 2027-12-01 | [21 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
22 | potential | Lead | CatOX | 0 | 0 | 0 | Gate Plan | 2027-06-01 | 2027-12-01 | [16 empty] | G1 |  | G2 |  |  |  | G3 |  |  |  |  | G4 | [5 empty] | G5 | [5 empty] | G6

## Kanara V00
Kanara | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-14 | SUM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.8 | 6.8 | 9.2 | 13.2 | 13.2 | 13.2 | 13.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 11.5 | 11 | 11 | 11 | 10.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Plan | Lead | Kanara | Engineering | * Manager | * Eng Manager | JiYoung Son | 2027-07-30 | 2027-12-27 | [13 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Plan | Lead | Kanara | PMO | * Manager | * Manager | Jinney Lee | 2027-07-30 | 2027-12-27 | [13 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
3 | Plan | Lead | Kanara | PMO | PM | PM | Project manager | 2027-07-30 | 2027-12-27 | [13 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
4 | Plan | Lead | Kanara | NPI IS | * Manager | * Manager | Dorothy Noh | 2027-07-30 | 2027-12-27 | [13 empty] | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
5 | Plan | Lead | Kanara | NPI IS | System □ | Leader | Tech Lead | 2027-07-30 | 2027-12-27 | [13 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Plan | Lead | Kanara | NPI IS | System □ | System engineer | System engineer | 2027-07-30 | 2027-12-27 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Plan | Lead | Kanara | NPI IS | System □ | System engineer | System engineer | 2027-07-30 | 2027-12-27 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
8 | Plan | Lead | Kanara | NPI IS | System □ | System engineer | System engineer | 2027-07-30 | 2027-12-27 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Plan | Lead | Kanara | NPI IS | System □ | Service engineer | Service engineer | 2027-07-30 | 2027-12-27 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
11 | Plan | Lead | Kanara | NPI IS | Mechanical | Leader | Jeremy Park | 2027-07-30 | 2027-12-27 | [13 empty] | 0.1 | 0.1 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
12 | Plan | Lead | Kanara | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-07-30 | 2027-12-27 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
13 | Plan | Lead | Kanara | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-07-30 | 2027-12-27 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
14 | Plan | Lead | Kanara | NPI IS | Mechanical | Mechanical engineer | Mechanical engineer | 2027-07-30 | 2027-12-27 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | Plan | Lead | Kanara | Control Eng. | * Manager | * Manager | Mogen Seo | 2027-07-30 | 2027-12-27 | [13 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
16 | Plan | Lead | Kanara | Control Eng. | Software | Leader | Gerald Park | 2027-07-30 | 2027-12-27 | [13 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
17 | Plan | Lead | Kanara | Control Eng. | Software | Software engineer | Software engineer | 2027-07-30 | 2027-12-27 | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
18 | Plan | Lead | Kanara | Control Eng. | Software | SW test engineer | SW test engineer | 2027-07-30 | 2027-12-27 | [20 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
19 | Plan | Lead | Kanara | Control Eng. | Electrical | Leader | Joshua Im | 2027-07-30 | 2027-12-27 | [15 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
20 | Plan | Lead | Kanara | Control Eng. | Electrical | Electrical engineer | Julia Mun | 2027-07-30 | 2027-12-27 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
21 | Plan | Lead | Kanara | Control Eng. | Electrical | Electrical engineer | Electrical engineer | 2027-07-30 | 2027-12-27 | [15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
22 | Plan | Lead | Kanara | 0 | 0 | 0 | Gate Plan | 2027-07-30 | 2027-12-27 | [13 empty] | G1 |  |  | G2 |  |  |  |  | G3/G4 |  |  |  |  | G5 |  |  |  |  | G6

## EUV Zenith Plus V00
EUV Zenith Plus | 406372 |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-02 | SUM | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Complete | Launched | EUV Zenith Plus | PMO | * Manager | * Manager | Jinney Lee | 2025-11-30 | 2026-06-30 | 0.2
2 | Complete | Launched | EUV Zenith Plus | PMO | PM | PM | Yuro Lee | 2025-11-30 | 2026-06-30 | 0.2
3 | Complete | Launched | EUV Zenith Plus | NPI IS | * Manager | * Manager | Dorothy Noh | 2025-11-30 | 2026-06-30 | 0.2
4 | Complete | Launched | EUV Zenith Plus | 0 | 0 | 0 | Gate Plan | 2025-11-30 | 2026-06-30 | G6

## Carl Zeiss. V00_Cancel
Carl Zeiss | TBC |  | 자동입력 | Resource Plan | Ver. | 0 | Date | 2025-07-09 | SUM | 0 | 0 | 0 | 0 | 4.5 | 6.5 | 8.5 | 9 | 9 | 9 | 9 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Status | Project Lifecycle | Project | Resource Department | Sub-Team | Resource Role | Name | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28
1 | Cancelled | Lead | Carl Zeiss | PMO | * Manager | * Manager | Jinney Lee | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
2 | Cancelled | Lead | Carl Zeiss | PMO | PM | PM | Project manager | [6 empty] | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7
3 | Cancelled | Lead | Carl Zeiss | NPI IS | * Manager | * Manager | Dorothy Noh | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
4 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | Tech Lead | Michael Kim | [6 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | Cancelled | Lead | Carl Zeiss | NPI IS | System □ | System engineer | System engineer | [6 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
6 | Cancelled | Lead | Carl Zeiss | NPI IS | System 1 | Service engineer | Judy Lee | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
7 | Cancelled | Lead | Carl Zeiss | NPI IS | Mechanical | Leader | Jeremy Park | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
8 | Cancelled | Lead | Carl Zeiss | NPI IS | Mechanical | Mechanical engineer | Jayden Lee | [6 empty] | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
9 | Cancelled | Lead | Carl Zeiss | Control Eng. | * Manager | * Manager | Mogen Seo | [6 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
10 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | Leader | Gerald Park | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
11 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | Software engineer | Software engineer | [6 empty] | 0.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 1 | 1 | 1
12 | Cancelled | Lead | Carl Zeiss | Control Eng. | Software | SW test engineer | SW test engineer | [7 empty] | 0.5 | 0.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5
13 | Cancelled | Lead | Carl Zeiss | Control Eng. | Electrical | Leader | Joshua Im | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
14 | Cancelled | Lead | Carl Zeiss | Control Eng. | Electrical | Electrical engineer | Electrical engineer | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
15 | Cancelled | Lead | Carl Zeiss | 0 | 0 | 0 | Gate Plan | [6 empty] | G2 | [9 empty] | G5

## <
[IO No] | LPLN1 |  | Resource Plan | Ver. | 0 | Date | 2025-07-02
No | Status | Project | Name | Resource Department | Resource Role | Sub-Team | G5 | G6 | 2025-06-25 | 2025-07-25 | 2025-08-25 | 2025-09-25 | 2025-10-25 | 2025-11-25 | 2025-12-25 | 2025-01-26 | 2025-02-26 | 2025-03-26 | 2025-04-26 | 2025-05-26 | 2025-06-26 | 2025-07-26 | 2025-08-26 | 2025-09-26 | 2025-10-26 | 2025-11-26 | 2025-12-26 | 2025-01-27 | 2025-02-27 | 2025-03-27 | 2025-04-27 | 2025-05-27 | 2025-06-27 | 2025-07-27 | 2025-08-27 | 2025-09-27 | 2025-10-27 | 2025-11-27 | 2025-12-27 | 2025-01-28 | 2025-02-28 | 2025-03-28 | 2025-04-28 | 2025-05-28 | 2025-06-28 | 2025-07-28 | 2025-08-28 | 2025-09-28 | 2025-10-28 | 2025-11-28 | 2025-12-28